## UnDope Development Budget
Cost
Infrastructure |  | 611984
Unity Licenses for tools |  | 66046 | Unity licence | 33023 | 2 units | #Installs | 2
Unity Cloud Storage |  | 11578 | Monthly fee | 827 | 6 units | Months | 14
Unity Collaboration |  | 24360 | Monthly fee | 1740 | 6 units | Months | 14
Hardware |  | 510000 | Laptops and Media Center Workstations(expected spec: i7 12th gen processor: Ryzen 7 6800H or above; ram: 16GB or above; GPU: RTX3060) | 85000 | 6 Units | #Units | 6
*rates are approximation converted from USD to INR
| Hours | Cost | Description of unit | Your adjusted input |  | Stipend
Concept & research | 176 | 30000 | Total Days | 44 |  | Monthly | 15000 | 90000 | 1260000
Game mechanics | 60 | 10227.2727 | Days | 15 |  | Weekly | 3750
Narrative, story | 32 | 5454.5455 | Days | 8 |  | Daily | 681.8182 | 22 days per month
Paper prototype | 28 | 4772.7273 | Days | 7 |  | Hourly | 170.4545
Concept art, mood images, sound examples | 56 | 9545.4545 | Days | 14
*rates are approximation converted from USD to INR | [5 empty] | https://www.ambitionbox.com/profile/game-developer-intern-salary
Content | 236 | 40230 | Total Days | 59
x levels, scenes, backgrounds | 80 | 13636.3636 | Days | 20
x characters | 60 | 10227.2727 | Days | 15
Songs, background music, soundtrack | 28 | 4772.7273 | Days | 7
Sound effects | 20 | 3409.0909 | Days | 5
Visual special effects | 20 | 3409.0909 | Days | 5
Translations | 28 | 4772.7273 | Days | 7
Implementation | 712 | 121363.6364 | Total Days | 178 |  | Project duration
Basic game program | 120 | 20454.5455 | Days | 30 |  | Months | 14
Build pipeline for daily deployments | 20 | 3409.0909 | Days | 5
User interfaces, UX, flow, menus | 88 | 15000 | Days | 22
Control scheme, keyboard, controller, touch | 20 | 3409.0909 | Days | 5
2D/3D engine setup | 16 | 2727.2727 | Days | 4 |  |  | .
Logic for game mechanics | 120 | 20454.5455 | Days | 30
Savegames | 60 | 10227.2727 | Days | 15
Multi-player game server | 88 | 15000 | Days | 22
Leaderboard, game center | 20 | 3409.0909 | Days | 5
Internationalization, localization functions | 20 | 3409.0909 | Days | 5
Art assets (sprites, etc.) | 60 | 10227.2727 | Days | 15
3D models | 80 | 13636.3636 | Days | 20
Purchasing Assest and 3D models |  | 41360
Pitching marketing | 68 | 21600 | Total Days | 17
Trailer, video clip | 40 | 6818.1818 | Days | 10
Website design | 28 | 4772.7273 | Days | 7
Website licenses, hosting, domain |  | 10000 | Licenses & fees | 10000
QA | 60 | 10230 | Total Days | 15
Quality control | 32 | 5454.5455 | Days | 8
Testing | 28 | 4772.7273 | Days | 7
| Hours | Cost |  | Days total | Months total
Expenses by Team | 1252 | 1260000 |  | 313 | 14.2273
Project cost |  | 663344
Subtotal | 1252 | 1923344 |  | 313 | 14.2273
GST/Taxes if applicable
Total * |  | 1923344
*rates are approximation converted from USD to INR

## Sheet2
Infrastructure |  | 576050
Unity Licenses for tools |  | 66046 | Unity licence | 33023 | #Installs | 2
Unity Cloud Storage |  | 0 | Monthly fee | 827 | Months
Unity Collaboration |  | 0 | Monthly fee | 1740 | Months
Hardware |  | 510000 | Laptops and Media Center Workstations(expected spec: i7 13th gen processor: Ryzen 7 6800H or above; ram: 16GB or above; GPU: RTX3060) | 85000 | #Units | 6
*rates are approximation converted from USD to INR
| Hours | Cost | Description of unit | Your adjusted input |  | Salaries
Concept & research | 164 | 0 | Total Days | 41 |  | Monthly | 17500 | 105000
Game mechanics | 56 | 0 | Days | 14 |  | Weekly | 4375
Narrative, story | 32 | 0 | Days | 8 |  | Daily | 795.4545 | 22 days per month
Paper prototype | 20 | 0 | Days | 5 |  | Hourly | 198.8636
Concept art, mood images, sound examples | 56 | 0 | Days | 14
*rates are approximation converted from USD to INR
Implementation | 712 | 0 | Total Days | 178 |  | Project duration
Basic game program | 120 | 0 | Days | 30 |  | Months | 13
Build pipeline for daily deployments | 20 | 0 | Days | 5
User interfaces, UX, flow, menus | 88 | 0 | Days | 22
Control scheme, keyboard, controller, touch | 20 | 0 | Days | 5
2D/3D engine setup | 16 | 0 | Days | 4 |  |  | .
Logic for game mechanics | 120 | 0 | Days | 30
Savegames | 60 | 0 | Days | 15
Multi-player game server | 88 | 0 | Days | 22
Leaderboard, game center | 20 | 0 | Days | 5
Internationalization, localization functions | 20 | 0 | Days | 5
Art assets (sprites, etc.) | 60 | 0 | Days | 15
3D models | 80 | 0 | Days | 20
Purchasing Assest and 3D models
Pitching marketing | 68 | 10000 | Total Days | 17
Trailer, video clip | 40 | 0 | Days | 10
Website design | 28 | 0 | Days | 7
Website licenses, hosting, domain |  | 10000 | Licenses & fees | 10000
Content | 236 | 0 | Total Days | 59
x levels, scenes, backgrounds | 80 | 0 | Days | 20
x characters | 60 | 0 | Days | 15
Songs, background music, soundtrack | 28 | 0 | Days | 7
Sound effects | 20 | 0 | Days | 5
Visual special effects | 20 | 0 | Days | 5
Translations | 28 | 0 | Days | 7
QA | 60 | 0 | Total Days | 15
Quality control | 32 | 0 | Days | 8
Testing | 28 | 0 | Days | 7
| Hours | Cost |  | Days total | Months total
Expenses by Team | 1240 | 1479545.455 |  | 310 | 14.0909
Project cost |  | 586050
Subtotal | 1240 | 2065595.455 |  | 310 | 14.0909
GST/Taxes if applicable |  | =
Total * |  | 2065595.455